## Timeline
Event Planning Checklist
Done? | Date Comp | Time Frame | Pre-Planning | Notes
Date of event is always Wednesday after Father's Day
|  | 24-18 months prior | Research potential city locations
|  | 24-18 months prior | Narrow down to one location
|  | 24-18 months prior | Research potential resorts in location | typically has a spa on site, restaurant options, ideally within walking distance to shops or restaurants
|  | 24-18 months prior | Narrow down to top 3-4 resorts
|  | 24-18 months prior | Contact resorts for proposals
|  | 24-18 months prior | Compare proposals to budget
|  | 24-18 months prior | Plan site visits
|  | 24-18 months prior | Conduct site visits and evaluate properties
24-18 months prior
|  | 18-12 months prior | Sign contract with location if not done so already
|  | 18-12 months prior | Run through general flow of meeting with RVP to get an idea of what needs to be done
|  | 18-12 months prior | Begin looking at options for entertainment
18-12 months prior
|  | 12 - 9 months prior | Send out calendar invite to DVPs, DivCons, DCs, DMs, ACs, ERO after previous Retreat ends
12 - 9 months prior
12 - 9 months prior
12 - 9 months prior
12 - 9 months prior
|  | 9 - 6 months prior | Reach out to possible Entertainment | Watch a show if possible
|  | 9 - 6 months prior | Research Team Building Activities
|  | 9 - 6 months prior | Get a vision of what the meeting will look like and rentals, items neded, etc | Reach out to hotel contact for list of approved vendors
|  | 9 - 6 months prior | Work with AV company to get idea of what will be needed
9 - 6 months prior
|  | 6 months prior | Send out Save the Date
|  | 6 months prior | Solidify Team Building activities and sign agreement
|  | 6 months prior | Research dinner locations
|  | 6 months prior | Research awards and get samples
6 months prior
|  | 5 months prior | Determine employee gifts
|  | 5 months prior | Determine spouse or children's activities - if doing
|  | 5 months prior | Determine name tag layout
|  | 5 months prior | Order key cards
5 months prior
|  | 4 months prior | Send out registration link no later than end of February
|  | 4 months prior | Send out separate link/email for Landfill
4 months prior
4 months prior
4 months prior
|  | 3 months prior | Visit location for final walk through
|  | 3 months prior | Send out last call for those who have not filled out registration
|  | 3 months prior | Collect size information for gifts
|  | 3 months prior | Find transportation company for airport to/from
|  | 3 months prior | Send name tags to be printed
|  | 3 months prior | Finalize head counts for dinner locations and solidify
|  | 3 months prior | Finalize menus for events
|  | 3 months prior | Get list of award winners and order final awards
3 months prior
3 months prior
|  | 3 months prior | Start rough draft of agenda and welcome letter | main Retreat and Landfill meeting
|  | 2 months prior | Finalize all gift choices and place order
2 months prior
2 months prior
2 months prior
2 months prior
|  | 1 month prior | Find rental vehicle to transport items to location
|  | 1 month prior | Get first draft of rooming list to hotel
|  | 1 month prior | Finalize agenda and welcome letter - send to printer
1 month prior
1 month prior
Done? | Date Comp | Time | Month-Of | Notes
Gather all items needed in one place and take inventory
Check for employee birthdays that will occur during dates
Team meeting - go over agenda, ask for volunteers or explain job assignments so they are prepared
Done? | Date Comp | Time | Week Before | Notes
Team meeting - go over job assignments
Get remote access for laptop
Done? | Date Comp | Time | Day Prior to Departure | Notes
Change Door Unlock Timers
Update voice mail and e-mail auto-reply message
Update Web sites that you manage
Give or throw away perishables from refrigerator
Done? | Date Comp | Time | Day of Departure | Notes
Done? | Date Comp | Time | Week of The Event | Notes
Team Meeting
Pre-Con with hotel staff, DMC, etc

## Master Folder Contents
Done? | Folder | Notes
| Personal daily schedule in front |  | List needs to be organized for ease of use
Agreements - ALL
Rooming List Copy
Hotel confirmations - get list that includes room numbers when all are checked in
Registration Copy
Agenda Copy
Welcome Letter Copy
Team Building Information
Dinner Reservation Information
Transportation Manifest
Awards list
BEOs
AV
Landfill section
Size list, just in case
Copy of presentation slides

## Packing List
Done? | Packing | Notes
| In checked luggage: |  | List needs to be organized for ease of use
Swag:
~ Shirts
~ Pullovers
~ Team Building team identifier
~ Gift
~ Gift
~ Gift
Welcome Letters
Agendas
Name Badges
Lanyards
Permanent Markers
Highlighters
Extra Pens
Sunscreen
Insect repellent
First aid kit
Mini sewing repair kit
Travel chargers
Foamboard signs
Banners
Gobo lighting screen
Easels
Cornhole boards
Ensure key cards are at hotel
Spouse/Kid activity invitations
Coolers
Kids welcome toys
Beach chairs
Footballs
Awards
Tip for band
Trophy for DOY
Flip Charts/Markers
Charging station
iPad

## Personal Packing
Done? | Packing | Notes
In checked luggage:
Shoes (walking/dress/beach/hiking)
Swimsuits
Exercise clothing
Sweaters, coats, hats, gloves
Comb/brush
Shampoo, hairspray
Hair dryer
Deodorant
Lotions/creams
Cosmetics
Shaving cream, shaver
Nail clippers, emery board
Toothbrush/paste/floss
Sunscreen
Insect repellent
First aid kit
Mini sewing repair kit
Travel plugs/adapters if leaving country
Travel alarm clock
Extra luggage space for purchases
In carry-on luggage:
Prescription medications
Vitamins and over-the-counter medications (travel sickness, headache, indigestion, diarrhea)
Extra pairs of sunglasses, prescription glasses, contact lenses
Address book/PDA and PDA charger
Cell phone and charger
Camera, video camera, film, batteries, binoculars
Magazines, books, portable music or DVD player, playing cards
Travel maps, guidebook, phrase book
Travel neck pillow
Snacks and bottled water
Lip balm
Towelettes
Ear plugs
Credit cards
Health insurance card
Long distance phone card
Driver's license
Auto insurance policy number and agent telephone number
Passport/visa
Recent photos of all travel companions
Local currency
Traveler's checks
Airplane tickets
Confirmation numbers for hotel, rental car, and other reservations